## Client
ITERATION 1
| R | A | D | I | T
Fran (Requirements and Analisys) | 2 | 2
Amin (Requirements and Analisys) | 2 | 2
Alejandro (Design and Implementations) |  |  | 1 | 2
Martin (Design and Implementations) |  |  | 1 | 2
Ece (Design and Implementations) |  |  | 1 | 1
Inci (Testing) |  |  |  |  | 3
Javier (Testing) |  |  |  |  | 2
Cost | 1015
Hours | 21
ITERATION 2
| R | A | D | I | T
Fran (Requirements and Analisys) | 2 | 2
Amin (Requirements and Analisys) | 1 | 2
Alejandro (Design and Implementations) |  |  | 1 | 1
Martin (Design and Implementations) |  |  | 1 | 2
Ece (Design and Implementations) |  |  | 1 | 4
Inci (Testing) |  |  |  |  | 3
Javier (Testing) |  |  |  |  | 2
Cost | 965
Hours | 22
ITERATION 3
| R | A | D | I | T
Fran (Requirements and Analisys) | 1 | 2
Amin (Requirements and Analisys) | 1 | 2
Alejandro (Design and Implementations) |  |  | 3 | 1
Martin (Design and Implementations) |  |  | 1 | 2
Ece (Design and Implementations) |  |  | 1 | 3
Inci (Testing) |  |  |  |  | 3
Javier (Testing) |  |  |  |  | 3
Cost | 960
Hours | 23
ITERATION 4
| R | A | D | I | T
Fran (Requirements and Analisys) | 2 | 2
Amin (Requirements and Analisys) | 1 | 2
Alejandro (Design and Implementations) |  |  | 1 | 1
Martin (Design and Implementations) |  |  | 1 | 2
Ece (Design and Implementations) |  |  |  | 3
Inci (Testing) |  |  |  |  | 2
Javier (Testing) |  |  |  |  | 3
Cost | 890
Hours | 20
ITERATION 5
| R | A | D | I | T
Fran (Requirements and Analisys) | 1 | 2
Amin (Requirements and Analisys) | 2 | 1
Alejandro (Design and Implementations) |  |  | 1 | 2
Martin (Design and Implementations) |  |  | 1 | 3
Ece (Design and Implementations) |  |  | 2 | 2
Inci (Testing) |  |  |  |  | 2
Javier (Testing) |  |  |  |  | 3
Cost | 955
Hours | 22
ITERATION 6
| R | A | D | I | T
Fran (Requirements and Analisys) | 2 | 2
Amin (Requirements and Analisys) | 2 | 2
Alejandro (Design and Implementations) |  |  | 1 | 1
Martin (Design and Implementations) |  |  | 1 | 2
Ece (Design and Implementations) |  |  | 2 | 3
Inci (Testing) |  |  |  |  | 3
Javier (Testing) |  |  |  |  | 3
Cost | 1100
Hours | 24
ITERATION 7
| R | A | D | I | T
Fran (Requirements and Analisys) | 1
Amin (Requirements and Analisys) | 1 | 1
Alejandro (Design and Implementations) |  |  | 2 | 1
Martin (Design and Implementations) |  |  | 1 | 3
Ece (Design and Implementations) |  |  | 1 | 3
Inci (Testing) |  |  |  |  | 4
Javier (Testing) |  |  |  |  | 3
Cost | 775
Hours | 21
ITERATION 8
| R | A | D | I | T
Fran (Requirements and Analisys) | 1 | 2
Amin (Requirements and Analisys) | 1 | 2
Alejandro (Design and Implementations) |  |  | 1 | 3
Martin (Design and Implementations) |  |  | 1 | 3
Ece (Design and Implementations) |  |  | 1 | 3
Inci (Testing) |  |  |  |  | 2
Javier (Testing) |  |  |  |  | 2
Cost | 895
Hours | 22
ITERATION 9
| R | A | D | I | T
Fran (Requirements and Analisys) | 2 | 3
Amin (Requirements and Analisys) | 1 | 3
Alejandro (Design and Implementations) |  |  | 1 | 1
Martin (Design and Implementations) |  |  |  | 2
Ece (Design and Implementations) |  |  | 1 | 3
Inci (Testing) |  |  |  |  | 1
Javier (Testing) |  |  |  |  | 2
Cost | 970
Hours | 20
ITERATION 10
| R | A | D | I | T
Fran (Requirements and Analisys) | 2 | 1
Amin (Requirements and Analisys) | 2 | 2
Alejandro (Design and Implementations) |  |  | 1 | 1
Martin (Design and Implementations) |  |  |  | 3
Ece (Design and Implementations) |  |  | 1 | 2
Inci (Testing) |  |  |  |  | 3
Javier (Testing) |  |  |  |  | 2
Cost | 930
Hours | 20
ITERATION 11
| R | A | D | I | T
Fran (Requirements and Analisys) | 1 | 2
Amin (Requirements and Analisys) | 1 | 2
Alejandro (Design and Implementations) |  |  | 1 | 3
Martin (Design and Implementations) |  |  | 1 | 3
Ece (Design and Implementations) |  |  | 1 | 3
Inci (Testing) |  |  |  |  | 4
Javier (Testing) |  |  |  |  | 3
Cost | 955
Hours | 25
ITERATION 12
| R | A | D | I | T
Fran (Requirements and Analisys) | 2 | 4
Amin (Requirements and Analisys) | 2 | 3
Alejandro (Design and Implementations) |  |  | 1 | 3
Martin (Design and Implementations) |  |  | 1 | 3
Ece (Design and Implementations) |  |  | 1 | 3
Inci (Testing) |  |  |  |  | 2
Javier (Testing) |  |  |  |  | 3
Cost | 1295
Hours | 28
ITERATION 13
| R | A | D | I | T
Fran (Requirements and Analisys) | 1 | 3
Amin (Requirements and Analisys) | 2 | 3
Alejandro (Design and Implementations) |  |  | 1 | 1
Martin (Design and Implementations) |  |  | 1 | 2
Ece (Design and Implementations) |  |  | 2 | 3
Inci (Testing) |  |  |  |  | 4
Javier (Testing) |  |  |  |  | 4
Cost | 1170
Hours | 27
ITERATION 14
| R | A | D | I | T
Fran (Requirements and Analisys) | 2 | 3
Amin (Requirements and Analisys) | 2 | 3
Alejandro (Design and Implementations) |  |  | 1 | 4
Martin (Design and Implementations) |  |  | 1 | 3
Ece (Design and Implementations) |  |  | 1 | 3
Inci (Testing) |  |  |  |  | 3
Javier (Testing) |  |  |  |  | 4
Cost | 1300
Hours | 30
ITERATION 15
| R | A | D | I | T
Fran (Requirements and Analisys) | 2 | 3
Amin (Requirements and Analisys) | 3 | 2
Alejandro (Design and Implementations) |  |  | 1 | 2
Martin (Design and Implementations) |  |  | 1 | 4
Ece (Design and Implementations) |  |  | 2 | 1
Inci (Testing) |  |  |  |  | 2
Javier (Testing) |  |  |  |  | 2
Cost | 1255
Hours | 25
ITERATION 16
| R | A | D | I | T
Fran (Requirements and Analisys) | 2 | 2
Amin (Requirements and Analisys) | 2 | 2
Alejandro (Design and Implementations) |  |  | 1 | 3
Martin (Design and Implementations) |  |  | 1 | 3
Ece (Design and Implementations) |  |  | 1 | 3
Inci (Testing) |  |  |  |  | 2
Javier (Testing) |  |  |  |  | 3
Cost | 1115
Hours | 25
ITERATION 17
| R | A | D | I | T
Fran (Requirements and Analisys) | 1 | 4
Amin (Requirements and Analisys) | 2 | 4
Alejandro (Design and Implementations) |  |  | 1 | 2
Martin (Design and Implementations) |  |  | 1 | 2
Ece (Design and Implementations) |  |  | 2 | 3
Inci (Testing) |  |  |  |  | 3
Javier (Testing) |  |  |  |  | 3
Cost | 1275
Hours | 28
ITERATION 18
| R | A | D | I | T
Fran (Requirements and Analisys) | 2 | 2
Amin (Requirements and Analisys) | 2 | 3
Alejandro (Design and Implementations) |  |  | 1 | 4
Martin (Design and Implementations) |  |  | 1 | 1
Ece (Design and Implementations) |  |  | 1 | 2
Inci (Testing) |  |  |  |  | 2
Javier (Testing) |  |  |  |  | 2
Cost | 1105
Hours | 23
ITERATION 19
| R | A | D | I | T
Fran (Requirements and Analisys) | 1 | 2
Amin (Requirements and Analisys) | 1 | 2
Alejandro (Design and Implementations) |  |  | 1 | 4
Martin (Design and Implementations) |  |  | 1 | 3
Ece (Design and Implementations) |  |  | 3 | 3
Inci (Testing) |  |  |  |  | 4
Javier (Testing) |  |  |  |  | 5
Cost | 1120
Hours | 30
ITERATION 20
| R | A | D | I | T
Fran (Requirements and Analisys) | 1 | 1
Amin (Requirements and Analisys) | 2 | 1
Alejandro (Design and Implementations) |  |  | 2 | 3
Martin (Design and Implementations) |  |  | 3 | 3
Ece (Design and Implementations) |  |  |  | 4
Inci (Testing) |  |  |  |  | 4
Javier (Testing) |  |  |  |  | 5
Cost | 1100
Hours | 29
ITERATION 21
| R | A | D | I | T
Fran (Requirements and Analisys) | 2 | 2
Amin (Requirements and Analisys) | 2 | 3
Alejandro (Design and Implementations) |  |  | 1 | 3
Martin (Design and Implementations) |  |  | 1 | 3
Ece (Design and Implementations) |  |  | 1 | 3
Inci (Testing) |  |  |  |  | 3
Javier (Testing) |  |  |  |  | 3
Cost | 1195
Hours | 27
ITERATION 22
| R | A | D | I | T
Fran (Requirements and Analisys) | 2 | 2
Amin (Requirements and Analisys) | 1 | 3
Alejandro (Design and Implementations) |  |  | 1 | 3
Martin (Design and Implementations) |  |  | 1 | 3
Ece (Design and Implementations) |  |  | 1 | 3
Inci (Testing) |  |  |  |  | 2
Javier (Testing) |  |  |  |  | 1
Cost | 1035
Hours | 23
ITERATION 23
| R | A | D | I | T
Fran (Requirements and Analisys) | 2 | 2
Amin (Requirements and Analisys) | 2 | 3
Alejandro (Design and Implementations) |  |  | 2 | 3
Martin (Design and Implementations) |  |  | 2 | 3
Ece (Design and Implementations) |  |  | 1 | 3
Inci (Testing) |  |  |  |  | 2
Javier (Testing) |  |  |  |  | 2
Cost | 1255
Hours | 27
ITERATION 24
| R | A | D | I | T
Fran (Requirements and Analisys) | 2 | 2
Amin (Requirements and Analisys) | 2 | 2
Alejandro (Design and Implementations) |  |  | 1 | 3
Martin (Design and Implementations) |  |  | 1 | 2
Ece (Design and Implementations) |  |  | 2 | 1
Inci (Testing) |  |  |  |  | 2
Javier (Testing) |  |  |  |  | 2
Cost | 1070
Hours | 22
ITERATION 25
| R | A | D | I | T
Fran (Requirements and Analisys) | 1 | 2
Amin (Requirements and Analisys) | 1 | 2
Alejandro (Design and Implementations) |  |  | 2 | 1
Martin (Design and Implementations) |  |  | 2 | 2
Ece (Design and Implementations) |  |  |  | 3
Inci (Testing) |  |  |  |  | 3
Javier (Testing) |  |  |  |  | 3
Cost | 910
Hours | 22
ITERATION 26
| R | A | D | I | T
Fran (Requirements and Analisys) | 1 | 2
Amin (Requirements and Analisys) | 2 | 1
Alejandro (Design and Implementations) |  |  | 1 | 3
Martin (Design and Implementations) |  |  | 1 | 3
Ece (Design and Implementations) |  |  | 2 | 3
Inci (Testing) |  |  |  |  | 4
Javier (Testing) |  |  |  |  | 3
Cost | 1045
Hours | 26
ITERATION 27
| R | A | D | I | T
Fran (Requirements and Analisys) | 1 | 1
Amin (Requirements and Analisys) | 1 | 2
Alejandro (Design and Implementations) |  |  | 2 | 3
Martin (Design and Implementations) |  |  | 1 | 4
Ece (Design and Implementations) |  |  | 2 | 3
Inci (Testing) |  |  |  |  | 4
Javier (Testing) |  |  |  |  | 3
Cost | 1020
Hours | 27

## Server
ITERATION 1
| R | A | D | I | T
Fran (Requirements and Analisys) | 2 | 2
Amin (Requirements and Analisys) | 2 | 2
Alejandro (Design and Implementations) |  |  | 1 | 2
Martin (Design and Implementations) |  |  | 1 | 2
Ece (Design and Implementations) |  |  | 1 | 1
Inci (Testing) |  |  |  |  | 3
Javier (Testing) |  |  |  |  | 2
Cost | 1015
Hours | 21
ITERATION 2
| R | A | D | I | T
Fran (Requirements and Analisys) | 2 | 2
Amin (Requirements and Analisys) | 1 | 2
Alejandro (Design and Implementations) |  |  | 1 | 1
Martin (Design and Implementations) |  |  | 1 | 2
Ece (Design and Implementations) |  |  | 1 | 4
Inci (Testing) |  |  |  |  | 3
Javier (Testing) |  |  |  |  | 2
Cost | 965
Hours | 22
ITERATION 3
| R | A | D | I | T
Fran (Requirements and Analisys) | 1 | 2
Amin (Requirements and Analisys) | 1 | 2
Alejandro (Design and Implementations) |  |  | 3 | 1
Martin (Design and Implementations) |  |  | 1 | 2
Ece (Design and Implementations) |  |  | 1 | 3
Inci (Testing) |  |  |  |  | 3
Javier (Testing) |  |  |  |  | 3
Cost | 960
Hours | 23
ITERATION 4
| R | A | D | I | T
Fran (Requirements and Analisys) | 2 | 2
Amin (Requirements and Analisys) | 1 | 2
Alejandro (Design and Implementations) |  |  | 1 | 1
Martin (Design and Implementations) |  |  | 1 | 2
Ece (Design and Implementations) |  |  |  | 3
Inci (Testing) |  |  |  |  | 2
Javier (Testing) |  |  |  |  | 3
Cost | 890
Hours | 20
ITERATION 5
| R | A | D | I | T
Fran (Requirements and Analisys) | 1 | 2
Amin (Requirements and Analisys) | 2 | 1
Alejandro (Design and Implementations) |  |  | 1 | 2
Martin (Design and Implementations) |  |  | 1 | 3
Ece (Design and Implementations) |  |  | 2 | 2
Inci (Testing) |  |  |  |  | 2
Javier (Testing) |  |  |  |  | 3
Cost | 955
Hours | 22
ITERATION 6
| R | A | D | I | T
Fran (Requirements and Analisys) | 2 | 2
Amin (Requirements and Analisys) | 2 | 2
Alejandro (Design and Implementations) |  |  | 1 | 1
Martin (Design and Implementations) |  |  | 1 | 2
Ece (Design and Implementations) |  |  | 2 | 3
Inci (Testing) |  |  |  |  | 3
Javier (Testing) |  |  |  |  | 3
Cost | 1100
Hours | 24
ITERATION 7
| R | A | D | I | T
Fran (Requirements and Analisys) | 1
Amin (Requirements and Analisys) | 1 | 1
Alejandro (Design and Implementations) |  |  | 2 | 1
Martin (Design and Implementations) |  |  | 1 | 3
Ece (Design and Implementations) |  |  | 1 | 3
Inci (Testing) |  |  |  |  | 4
Javier (Testing) |  |  |  |  | 3
Cost | 775
Hours | 21
ITERATION 8
| R | A | D | I | T
Fran (Requirements and Analisys) | 1 | 2
Amin (Requirements and Analisys) | 1 | 2
Alejandro (Design and Implementations) |  |  | 1 | 3
Martin (Design and Implementations) |  |  | 1 | 3
Ece (Design and Implementations) |  |  | 1 | 3
Inci (Testing) |  |  |  |  | 2
Javier (Testing) |  |  |  |  | 2
Cost | 895
Hours | 22
ITERATION 9
| R | A | D | I | T
Fran (Requirements and Analisys) | 2 | 3
Amin (Requirements and Analisys) | 1 | 3
Alejandro (Design and Implementations) |  |  | 1 | 1
Martin (Design and Implementations) |  |  |  | 2
Ece (Design and Implementations) |  |  | 1 | 3
Inci (Testing) |  |  |  |  | 1
Javier (Testing) |  |  |  |  | 2
Cost | 970
Hours | 20
ITERATION 10
| R | A | D | I | T
Fran (Requirements and Analisys) | 2 | 1
Amin (Requirements and Analisys) | 2 | 2
Alejandro (Design and Implementations) |  |  | 1 | 1
Martin (Design and Implementations) |  |  |  | 3
Ece (Design and Implementations) |  |  | 1 | 2
Inci (Testing) |  |  |  |  | 3
Javier (Testing) |  |  |  |  | 2
Cost | 930
Hours | 20
ITERATION 11
| R | A | D | I | T
Fran (Requirements and Analisys) | 1 | 2
Amin (Requirements and Analisys) | 1 | 2
Alejandro (Design and Implementations) |  |  | 1 | 3
Martin (Design and Implementations) |  |  | 1 | 3
Ece (Design and Implementations) |  |  | 1 | 3
Inci (Testing) |  |  |  |  | 4
Javier (Testing) |  |  |  |  | 3
Cost | 955
Hours | 25
ITERATION 12
| R | A | D | I | T
Fran (Requirements and Analisys) | 2 | 4
Amin (Requirements and Analisys) | 2 | 3
Alejandro (Design and Implementations) |  |  | 1 | 3
Martin (Design and Implementations) |  |  | 1 | 3
Ece (Design and Implementations) |  |  | 1 | 3
Inci (Testing) |  |  |  |  | 2
Javier (Testing) |  |  |  |  | 3
Cost | 1295
Hours | 28
ITERATION 13
| R | A | D | I | T
Fran (Requirements and Analisys) | 1 | 3
Amin (Requirements and Analisys) | 2 | 3
Alejandro (Design and Implementations) |  |  | 1 | 1
Martin (Design and Implementations) |  |  | 1 | 2
Ece (Design and Implementations) |  |  | 2 | 3
Inci (Testing) |  |  |  |  | 4
Javier (Testing) |  |  |  |  | 4
Cost | 1170
Hours | 27
ITERATION 14
| R | A | D | I | T
Fran (Requirements and Analisys) | 2 | 3
Amin (Requirements and Analisys) | 2 | 3
Alejandro (Design and Implementations) |  |  | 1 | 4
Martin (Design and Implementations) |  |  | 1 | 3
Ece (Design and Implementations) |  |  | 1 | 3
Inci (Testing) |  |  |  |  | 3
Javier (Testing) |  |  |  |  | 4
Cost | 1300
Hours | 30
ITERATION 15
| R | A | D | I | T
Fran (Requirements and Analisys) | 2 | 3
Amin (Requirements and Analisys) | 3 | 2
Alejandro (Design and Implementations) |  |  | 1 | 2
Martin (Design and Implementations) |  |  | 1 | 4
Ece (Design and Implementations) |  |  | 2 | 1
Inci (Testing) |  |  |  |  | 2
Javier (Testing) |  |  |  |  | 2
Cost | 1255
Hours | 25
ITERATION 16
| R | A | D | I | T
Fran (Requirements and Analisys) | 2 | 2
Amin (Requirements and Analisys) | 2 | 2
Alejandro (Design and Implementations) |  |  | 1 | 3
Martin (Design and Implementations) |  |  | 1 | 3
Ece (Design and Implementations) |  |  | 1 | 3
Inci (Testing) |  |  |  |  | 2
Javier (Testing) |  |  |  |  | 3
Cost | 1115
Hours | 25
ITERATION 17
| R | A | D | I | T
Fran (Requirements and Analisys) | 1 | 4
Amin (Requirements and Analisys) | 2 | 4
Alejandro (Design and Implementations) |  |  | 1 | 2
Martin (Design and Implementations) |  |  | 1 | 2
Ece (Design and Implementations) |  |  | 2 | 3
Inci (Testing) |  |  |  |  | 3
Javier (Testing) |  |  |  |  | 3
Cost | 1275
Hours | 28
ITERATION 18
| R | A | D | I | T
Fran (Requirements and Analisys) | 2 | 2
Amin (Requirements and Analisys) | 2 | 3
Alejandro (Design and Implementations) |  |  | 1 | 4
Martin (Design and Implementations) |  |  | 1 | 1
Ece (Design and Implementations) |  |  | 1 | 2
Inci (Testing) |  |  |  |  | 2
Javier (Testing) |  |  |  |  | 2
Cost | 1105
Hours | 23
ITERATION 19
| R | A | D | I | T
Fran (Requirements and Analisys) | 1 | 2
Amin (Requirements and Analisys) | 1 | 2
Alejandro (Design and Implementations) |  |  | 1 | 4
Martin (Design and Implementations) |  |  | 1 | 3
Ece (Design and Implementations) |  |  | 3 | 3
Inci (Testing) |  |  |  |  | 4
Javier (Testing) |  |  |  |  | 5
Cost | 1120
Hours | 30
ITERATION 20
| R | A | D | I | T
Fran (Requirements and Analisys) | 1 | 1
Amin (Requirements and Analisys) | 2 | 1
Alejandro (Design and Implementations) |  |  | 2 | 3
Martin (Design and Implementations) |  |  | 3 | 3
Ece (Design and Implementations) |  |  |  | 4
Inci (Testing) |  |  |  |  | 4
Javier (Testing) |  |  |  |  | 5
Cost | 1100
Hours | 29
ITERATION 21
| R | A | D | I | T
Fran (Requirements and Analisys) | 2 | 2
Amin (Requirements and Analisys) | 2 | 3
Alejandro (Design and Implementations) |  |  | 1 | 3
Martin (Design and Implementations) |  |  | 1 | 3
Ece (Design and Implementations) |  |  | 1 | 3
Inci (Testing) |  |  |  |  | 3
Javier (Testing) |  |  |  |  | 3
Cost | 1195
Hours | 27
ITERATION 22
| R | A | D | I | T
Fran (Requirements and Analisys) | 2 | 2
Amin (Requirements and Analisys) | 1 | 3
Alejandro (Design and Implementations) |  |  | 1 | 3
Martin (Design and Implementations) |  |  | 1 | 3
Ece (Design and Implementations) |  |  | 1 | 3
Inci (Testing) |  |  |  |  | 2
Javier (Testing) |  |  |  |  | 1
Cost | 1035
Hours | 23
ITERATION 23
| R | A | D | I | T
Fran (Requirements and Analisys) | 2 | 2
Amin (Requirements and Analisys) | 2 | 3
Alejandro (Design and Implementations) |  |  | 2 | 3
Martin (Design and Implementations) |  |  | 2 | 3
Ece (Design and Implementations) |  |  | 1 | 3
Inci (Testing) |  |  |  |  | 2
Javier (Testing) |  |  |  |  | 2
Cost | 1255
Hours | 27
ITERATION 24
| R | A | D | I | T
Fran (Requirements and Analisys) | 2 | 2
Amin (Requirements and Analisys) | 2 | 2
Alejandro (Design and Implementations) |  |  | 1 | 3
Martin (Design and Implementations) |  |  | 1 | 2
Ece (Design and Implementations) |  |  | 2 | 1
Inci (Testing) |  |  |  |  | 2
Javier (Testing) |  |  |  |  | 2
Cost | 1070
Hours | 22
ITERATION 25
| R | A | D | I | T
Fran (Requirements and Analisys) | 1 | 2
Amin (Requirements and Analisys) | 1 | 2
Alejandro (Design and Implementations) |  |  | 2 | 1
Martin (Design and Implementations) |  |  | 2 | 2
Ece (Design and Implementations) |  |  |  | 3
Inci (Testing) |  |  |  |  | 3
Javier (Testing) |  |  |  |  | 3
Cost | 910
Hours | 22
ITERATION 26
| R | A | D | I | T
Fran (Requirements and Analisys) | 1 | 2
Amin (Requirements and Analisys) | 2 | 1
Alejandro (Design and Implementations) |  |  | 1 | 3
Martin (Design and Implementations) |  |  | 1 | 3
Ece (Design and Implementations) |  |  | 2 | 3
Inci (Testing) |  |  |  |  | 4
Javier (Testing) |  |  |  |  | 3
Cost | 1045
Hours | 26
ITERATION 27
| R | A | D | I | T
Fran (Requirements and Analisys) | 1 | 1
Amin (Requirements and Analisys) | 1 | 2
Alejandro (Design and Implementations) |  |  | 2 | 3
Martin (Design and Implementations) |  |  | 1 | 4
Ece (Design and Implementations) |  |  | 2 | 3
Inci (Testing) |  |  |  |  | 4
Javier (Testing) |  |  |  |  | 3
Cost | 1020
Hours | 27

## PriceTable
TOTAL HOURS |  | PRICE PER HOUR | TOTAL PRICE
Requierments | 172 | 100 | 17200
Analisys | 234 | 60 | 14040
Desing | 194 | 50 | 9700
Implementation | 414 | 25 | 10350
Testing | 304 | 20 | 6080
Inception |  |  | 1500
Transition |  |  | 2000
TOTAL BUDGET |  |  | 60870

## EffortEstimation
CLIENT HOURS | FR1 | FR8 | FR15 | FR19 | FR20 | FR27 | FR2 | FR3 | FR5 | FR9 | FR10 | FR13 | FR14 | FR17 | FR21 | FR22 | FR23 | FR24 | FR25 | FR26 | FR4 | FR6 | FR7 | FR11 | FR12 | FR16 | FR18 | TOTAL
Requirements | 4 | 2 | 5 | 2 | 3 | 2 | 3 | 2 | 3 | 3 | 4 | 3 | 4 | 3 | 4 | 3 | 4 | 4 | 2 | 3 | 3 | 4 | 2 | 2 | 4 | 4 | 4 | 86
Analysis | 4 | 4 | 5 | 4 | 2 | 3 | 4 | 4 | 3 | 6 | 3 | 6 | 6 | 8 | 5 | 5 | 5 | 4 | 4 | 3 | 4 | 4 | 1 | 4 | 7 | 4 | 5 | 117
Design | 3 | 3 | 4 | 5 | 5 | 5 | 3 | 5 | 4 | 2 | 2 | 4 | 3 | 4 | 3 | 3 | 5 | 4 | 4 | 4 | 2 | 4 | 4 | 3 | 3 | 3 | 3 | 97
Implementation | 5 | 9 | 7 | 10 | 10 | 10 | 7 | 6 | 7 | 6 | 6 | 6 | 10 | 7 | 9 | 9 | 9 | 6 | 6 | 9 | 6 | 6 | 7 | 9 | 9 | 9 | 7 | 207
Testing | 5 | 4 | 4 | 9 | 9 | 7 | 5 | 6 | 5 | 3 | 5 | 8 | 7 | 6 | 6 | 3 | 4 | 4 | 6 | 7 | 5 | 6 | 7 | 7 | 5 | 5 | 4 | 152
TOTAL | 21 | 22 | 25 | 30 | 29 | 27 | 22 | 23 | 22 | 20 | 20 | 27 | 30 | 28 | 27 | 23 | 27 | 22 | 22 | 26 | 20 | 24 | 21 | 25 | 28 | 25 | 23 | 659
SERVER HOURS | FR1 | FR8 | FR15 | FR19 | FR20 | FR27 | FR2 | FR3 | FR5 | FR9 | FR10 | FR13 | FR14 | FR17 | FR21 | FR22 | FR23 | FR24 | FR25 | FR26 | FR4 | FR6 | FR7 | FR11 | FR12 | FR16 | FR18 | TOTAL
Requirements | 4 | 2 | 5 | 2 | 3 | 2 | 3 | 2 | 3 | 3 | 4 | 3 | 4 | 3 | 4 | 3 | 4 | 4 | 2 | 3 | 3 | 4 | 2 | 2 | 4 | 4 | 4 | 86
Analysis | 4 | 4 | 5 | 4 | 2 | 3 | 4 | 4 | 3 | 6 | 3 | 6 | 6 | 8 | 5 | 5 | 5 | 4 | 4 | 3 | 4 | 4 | 1 | 4 | 7 | 4 | 5 | 117
Design | 3 | 3 | 4 | 5 | 5 | 5 | 3 | 5 | 4 | 2 | 2 | 4 | 3 | 4 | 3 | 3 | 5 | 4 | 4 | 4 | 2 | 4 | 4 | 3 | 3 | 3 | 3 | 97
Implementation | 5 | 9 | 7 | 10 | 10 | 10 | 7 | 6 | 7 | 6 | 6 | 6 | 10 | 7 | 9 | 9 | 9 | 6 | 6 | 9 | 6 | 6 | 7 | 9 | 9 | 9 | 7 | 207
Testing | 5 | 4 | 4 | 9 | 9 | 7 | 5 | 6 | 5 | 3 | 5 | 8 | 7 | 6 | 6 | 3 | 4 | 4 | 6 | 7 | 5 | 6 | 7 | 7 | 5 | 5 | 4 | 152
TOTAL | 21 | 22 | 25 | 30 | 29 | 27 | 22 | 23 | 22 | 20 | 20 | 27 | 30 | 28 | 27 | 23 | 27 | 22 | 22 | 26 | 20 | 24 | 21 | 25 | 28 | 25 | 23 | 659
ELABORATION time (h) | 308
CONSTRUCTION time(h) | 1010
TOTAL HOURS | 1318
HOURS PER WEEK | 40

## Schedule
| 2025-11-13 |  |  |  | 2025-11-17 | [6 empty] | 2025-11-24 | [6 empty] | 2025-12-01 | [6 empty] | 2025-12-08 | [6 empty] | 2025-12-15 | [6 empty] | 2025-12-22 | [6 empty] | 2025-12-29
| WEEK 1 |  |  |  | WEEK 2 | [6 empty] | WEEK 3 | [6 empty] | WEEK 4 | [6 empty] | WEEK 5 | [6 empty] | WEEK 6 | [6 empty] | WEEK 7 | [6 empty] | WEEK 8
| THURSDAY | FRIDAY | SATURDAY | SUNDAY | MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | SATURDAY | SUNDAY | MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | SATURDAY | SUNDAY | MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | SATURDAY | SUNDAY | MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | SATURDAY | SUNDAY | MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | SATURDAY | SUNDAY | MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | SATURDAY | SUNDAY | MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | SATURDAY | SUNDAY
it1 |  | R/A/D | I/T
it2 |  | R/A/D | I/T
it3 |  | R/A/D | I/T
it4 |  |  |  |  | R/A | D |  | I | T
it5 |  |  |  |  | R/A | D |  | I | T
it6 |  |  |  |  | R/A | D |  | I | T
it7 | [11 empty] | R/A | D |  | I | T
it8 | [11 empty] | R/A | D |  | I | T
it9 | [11 empty] | R/A | D |  | I | T
it10 | [14 empty] | R/A | D |  |  | I | T
it11 | [14 empty] | R/A | D |  |  | I | T
it12 | [14 empty] | R/A | D |  |  | I | T
it13 | [18 empty] | R/A | D |  | I | T
it14 | [18 empty] | R/A | D |  | I | T
it15 | [18 empty] | R/A | D |  | I | T
it16 | [25 empty] | R/A | D |  | I | T
it17 | [25 empty] | R/A | D |  | I | T
it18 | [25 empty] | R/A | D |  | I | T
it19 | [32 empty] | R/A | D |  | I | T
it20 | [32 empty] | R/A | D |  | I | T
it21 | [32 empty] | R/A | D |  | I | T
it22 | [39 empty] | R/A | D |  | I | T
it23 | [39 empty] | R/A | D |  | I | T
it24 | [39 empty] | R/A | D |  | I | T
it25 | [46 empty] | R/A | D |  | I | T
it26 | [46 empty] | R/A | D |  | I | T
it27 | [46 empty] | R/A | D |  | I | T